## Tutor Sessions
Tutor Sessions time line
| Date of call | Days
1st session with tutor | 2012-10-08 | 1
2nd session with tutor | 2012-10-16 | 1
3rd session with tutor | 2012-10-26 | 1
4th session with tutor | 2012-11-12 | 1
5th session with tutor | 2012-11-21 | 1
6th session with tutor | 2012-12-03 | 1
7th session with tutor | 2012-12-21 | 1

## Documentation
Documentation Time Line
| Deadline | Days
Abstract writing | 2012-10-08 | 1
Compile Exp 1 Results | 2012-10-25 | 1
Compile Exp 2 Results | 2012-11-12 | 1
Compile Exp 3 Results | 2012-11-16 | 1
Compile Exp 4 Results | 2012-11-21 | 1
Compile Exp 5 Results | 2012-12-03 | 1
Compile Exp 6 Results | 2012-12-19 | 1

## Experiments
Experiments time line
| Start Date | Deadline | No. of days
Experiment 1 | 2012-10-13 | 2012-10-25 | 12
Experiment 2 | 2012-11-07 | 2012-11-12 | 5
Experiment 3 | 2012-11-12 | 2012-11-16 | 4
Experiment 4 | 2012-11-08 | 2012-11-21 | 13
Experiment 5 | 2012-11-25 | 2012-12-04 | 9
Experiment 6 | 2012-12-06 | 2012-12-13 | 7
Formulas:
Start Date = [Deadline]-[No. of days]

## Experiment 1
Experiment 1 time line
Experiment Start day | 2012-10-13
Experiment Deadline | 2012-10-25
Tasks
| Start Day | No. of days
Configuration : Configure one COSFIRE filter for each symbol model. | 2012-10-13 | 1
Training : For each symbol model image apply the 50 COSFIRE filters one by one. | 2012-10-14 | 2
Testing : For each testing symbol, we have to apply the 50 COSFIRE filters one by one. | 2012-10-15 | 5
Testing : Run data sets and count the number of TP and FP for each | 2012-10-19 | 4
Post-Experiment : Save operators to file in 2 different files, each corresponding to a specific list of Rho, as a check point | 2012-10-23 | 1
Post-Experiment : Save operators output to file in 2 different folders, each corresponding to a specific list of Rho, as a check point | 2012-10-23 | 1
Post-Experiment : Transpose final result so that we use a row vector (rather than column vector) to represent the responses achieved by 50 COSFIRE operators for each symbol. | 2012-10-23 | 1
Misc : Section code into separate Scripts. | 2012-10-24 | 1
Misc : Use tic toc commands to measure times of execution | 2012-10-25 | 1

## Experiment 2
Experiment 2 time line
Experiment Start day | 2012-11-07
Experiment Deadline | 2012-11-12
Tasks
| Start Day | No. of days
Pre-Experiment : Set deadlines for experiment 2 | 2012-11-07 | 1
Pre-Experiment : Download datasets | 2012-11-07 | 1
Pre-Experiment : Optimize Code | 2012-11-07 | 1
Configuration : Use code from experiment 1 to run configuration with less circles | 2012-11-08 | 1
Training : Run Training | 2012-11-08 | 1
Testing : Run testing for sketches25f-level1, sketches25f-level2 and sketches25f-level3 | 2012-11-09 | 3
Post-Experiments : Read data set's XML files to determine results and Re-run one experiment with different parameters, ( different versions of alpha ) | 2012-11-12 | 1

## Experiment 3
Experiment 3 time line
Experiment Start day | 2012-11-12
Experiment Deadline | 2012-11-16
Tasks
| Start Day | No. of days
Pre-Experiment : Setting parameters for rigidity (alpha = 0 and Sigma0=0) | 2012-11-12 | 1
Configuration : Run Configuration on specified datasets | 2012-11-12 | 1
Training : Run Training on specified datasets | 2012-11-12 | 1
Testing : Run Testing on specified datasets | 2012-11-13 | 3
Post-Experiment : Report Results | 2012-11-16 | 1

## Experiment 4
Experiment 4 time line
Experiment Start day | 2012-11-08
Experiment Deadline | 2012-11-21
Tasks
| Start Day | No. of days
Pre-Experiment : Setting Rho List to have fewer concentric circles | 2012-11-08 | 1
Configuration : Run Configuration on specified datasets | 2012-11-08 | 1
Training : Run Training on specified datasets | 2012-11-08 | 1
Testing : Run Testing on specified datasets | 2012-11-09 | 5
Post-Experiment : Report Results | 2012-11-21 | 1

## Experiment 5
Experiment 5 time line
Experiment Start day | 2012-11-25
Experiment Deadline | 2012-12-04
Tasks
| Start Day | No. of days
Pre-Experiment : Investigate errors when giving out different sets of rho lists. | 2012-11-25 | 1
Pre-Experiment : Set parameters according to best combinations from the previous experiments | 2012-11-25 | 1
Pre-Experiment : Tend to new code changes like exporting of Jpegs. | 2012-11-25 | 1
Pre-Experiment : Save result to file. | 2012-11-25 | 1
Pre-Experiment : Port rhoList viewer to MATLAB. | 2012-11-25 | 1
Pre-Experiment : Modify script as to run multiple datasets in one run. | 2012-11-25 | 1
Configuration : Run Configuration, all datasets | 2012-11-27 | 1
Training : Run Training, all datasets | 2012-11-27 | 1
Testing : Run Testing, all datasets & save each testing image vector | 2012-11-28 | 5
Post Experiment : Include Results, Conclusions etc. in the Results report | 2012-12-03 | 1
Post Experiment : Include code changes etc. to the specifications report | 2012-12-03 | 1
Post Experiment : Saving files | 2012-12-04 | 1

## Experiment 6
Experiment 6 time line
Experiment Start day | 2012-12-06
Experiment Deadline | 2012-12-13
Tasks
| Start Day | No. of days
Pre-Experiment : Make note of the changes done with George to lighten the process of configuration, (removing redundant tuples). | 2012-12-06 | 1
Pre-Experiment : Write program which checks the rho list against each model image. Making sure that each model image has at least 4 tuples in its operators. Mention this as pre-processing. | 2012-12-07 | 3
Pre-Experiment : Email Dr. Delalandre regarding the datasets. | 2012-12-07 | 1
Configuration : Run the configuration, all datasets | 2012-12-08 | 1
Training : Run the Training, all datasets | 2012-12-08 | 1
Testing : Run the Testing, all datasets | 2012-12-08 | 8
Post Experiment : Report results | 2012-12-18 | 1
Post Experiment : Report any changes | 2012-12-18 | 1
Post Experiment : Include code changes etc. to the specifications report | 2012-12-19 | 1